## Slide 1: Prepare to be unpopular Tips for shutting services down
Catherine Jones
Software Engineering Group Leader
STFC
#RSE18 4/9/2018

## Slide 2: Why me?
Long history of service close-down, major ones are:
  Replacing service I had written with commercial product
  Migrating national service (JISCMail) to new provider
  Closing down MRC Data Support Service (STFC provided)
  In process of closing CCPForge
Services and user needs do not stay static – they SHOULD come and go

## Slide 3: Why close a service?
Shutting software based services down is unglamorous
Sometimes you want to, sometimes you have to
Hard to do well BUT setting it up well, will help close it
Commercial
Not viable
Unsuccessful rebidding
Hardware
Software
Security
Strategic
Not core business
Resourcing
Closure vs Migration
Technology change
Technology outlier

## Slide 4: Before you start planning …..in an ideal world

## Slide 5: Who uses it, when and WHY?
Knowledge is power and vital to planning
Who
  Help identify best communication methods
  Help identify sources of potential negative feedback
When
  Is usage linked to time of year/specific process?
  Help identify best time to stop it
Why
  Signposting to other resources
  Training for better solutions
Understand your service better than anyone else
Run routine stats from the start

## Slide 6: Stakeholder support
Know your stakeholders
  Your Management
  Funders of the service
  Any reporting structure
  The users (and their management chain)
Get your management on board & keep them updated
  Ensure they can respond with your formal message if they get complaints
Don’t let your manager be ambushed, preparation is key
Ensure there are decision making/support structures which work for you

## Slide 7: Communicating service shut-down
There will always be a reason for stopping
  Have a short clear reason
  You may not want to tell all stakeholders everything
Writing a communication plan can help focus the message
  Writing FAQs can also help clarify difficult issues https://www.softeng-support.ac.uk/?q=documents/2018/04/10/ccpforge-faq.html
If you started the service – acknowledge that you may be personally upset to close it
If there isn’t a formal service definition – write one
Ensure your message is clear
Have a service definition & associated policies

## Slide 8: Planning and implementing

## Slide 9: Plan and Timelines
Migrating or handing back content takes lots of time
Estimate time commitment needed from users
Get plan approved by key stakeholders
If it is a well used service, allow over 6 months to shut it
Set a (realistic) date and stick to it
Over-estimate time for activities, especially if someone else is doing it
Use standard planning tools from the start

## Slide 10: Content
If there is content in your service
  Who owns it?
  What rights do you have as the service manager?
  Are the users internal or external?
  Is there formal content policy?
If you don’t have the rights, you may not be able to migrate it, modify it or even dispose of it.
How easy is it to get the content out in a standard format?
Understand what rights you have over the content before you start decommissioning
If content is involved have an agreement with users/providers from the start

## Slide 11: Communication
Regularly and with purpose, as short as possible
Every service has users that the help desk know well
  If you start to get significant feedback from quiet users, take it on board and adapt if necessary
Consider what you will do if you can’t contact significant users directly
Important to communicate through the close down/migration process
Set up communication channels from the start

## Slide 12: Statistics and Posterity
Before you start, do a last stats run
  Checks for successful content transfer
  Complete reporting periods for the records
What needs to be kept
  Institutional requirements/archiving
  Best practice for future
  Final reports
Remember you may not be entitled to keep things “just in case “ – GPDR/legal/institutional requirements
Do final statistics before any significant changes
Have a policy for service documentation creation and maintenance

## Slide 13: Once it is all over

## Slide 14: Actually turn everything off
Include decommissioning in your plan
  Equipment
  Help desk/specialist emails/twitter/UTube/Website
  Service documentation
  Mentions of the service on institutional websites
Signposting to the service
  How long for?
It will take longer than you think and you will forget something!
Have decommissioning as a activity in your plan
Document references to the service as you go

## Slide 15: Summary
Shutting software based services down is unglamorous
You will be unpopular with your keen users
Have a good reason and be able to articulate this
Plan and be realistic
Communicate regularly during the process
Tie up all the loose ends – they will come back to haunt you
Plan to shut down from the start - have your policy & stats in place
Closing down services professionally should be a badge of honour – it is harder than starting them

## Slide 16
Thanks for listening
Thanks to staff in the RAL & Chadwick Libraries, STFC JISCMail team and Software Engineering Group for helping me close and/or migrate services successfully over my career.
Catherine.jones@stfc.ac.uk
@Cm_j0nes